## Checklist
CHANGE DETAILS
Change Request Number# | CRQ | Implementation Date | 19 March 2020
HRHI Contact Details of Senior Resource | Michelle Chong | Cell # | 083 647 1181 | Work # | 011 631 7817
Has the change been Retro Fitted into DR | No | If "Yes" please provide change number |  | NA
Has the change been Retro Fitted into UAT | No | If "Yes" please provide change number |  | NA
Description of the change:
One World Appliaction Failover Tests
Impacted Systems / Services (Provide a comprehensive list of Systems and Services)
One World
Pre-Implementation Steps (Sequence of Events) | Start Time | End Time | Responsible Person | Area | Contact Details
19 March 2020 | 18h00
2020-03-19
Implementation Steps (Sequence of Events)
Log in to OneWorld Application Production Server | 18h00 | 18h05 | Stewart Fohlo | Risk IT | 061 468 2979
Stop OneOrld Application Services | 18h05 | 18h15 | Stewart Fohlo | Risk IT | 061 468 2979
Log in to OneWorld Application DR Server | 18h15 | 18h25 | Stewart Fohlo | Risk IT | 061 468 2979
Start OneWorld Application Services | 18h25 | 18h35 | Stewart Fohlo | Risk IT | 061 468 2979
Post Implementation Testing / Verification Steps (Sequence of Events)
Login and Test the Application | 18h35 | 19h00 | Stewart Fohlo | Risk IT | 061 468 2979
TEST ASSESSMENT
Has the change been tested in the Test Environment? | Yes | Tested during DB Upgrade
Has regression testing been successful? | No | N/A
Has the backout been tested in the test environment? | Yes | Yes
Has the change been tested & signed off by all impacted parties? | Yes | Yes
Has Business approval and TCR been Signed off, completed and Attached to the Remedy Change | Yes | N/A
BACKOUT / CONTINGENCY PLAN
Backout duration | 30 minutes
Backout / Contingency Tasks / Activities (Sequence of Events) | Start Time | End Time | Responsible Person | Area | Contact Details
Log in to DR application server and stop app services | 19h00 | 19h15 | Stewart Fohlo | Risk IT | 061 468 2979
Log in to Prod application server and start app services | 19h15 | 19h30 | Stewart Fohlo | Risk IT | 061 468 2979
Backout / Contingency Post Implementation Testing (Sequence of Events) | Start Time | End Time | Responsible Person | Area | Contact Details
Test if the Application is starting Up | 19h30 | 19h45 | Stewart Fohlo | Risk IT | 061 468 2979
Login to the Application and Navigate through the forms | 19h45 | 19h55 | Stewart Fohlo | Risk IT | 061 468 2979
Change Deployment Template