## Checklist
CHANGE DETAILS
Change Request Number# | CRQ000000082604 | Implementation Date | 19 March 2020
HRHI Contact Details of Senior Resource | Michelle Chong | Cell # | 083 647 1181 | Work # | 011 631 7817
Has the change been Retro Fitted into DR | No | If "Yes" please provide change number |  | NA
Has the change been Retro Fitted into UAT | No | If "Yes" please provide change number |  | NA
Description of the change:
InMagic Database Upgrade from MS SQL 2008 to MS SQL 2016
Impacted Systems / Services (Provide a comprehensive list of Systems and Services)
InMagic
Pre-Implementation Steps (Sequence of Events) | Start Time | End Time | Responsible Person | Area | Contact Details
19 March 2020
2020-03-19
Implementation Steps (Sequence of Events)
Vendor to perform the upgrade steps |  | 09h00 | Ilze Cloete | InMagic Vendor Support | 0713521987
Post Implementation Testing / Verification Steps (Sequence of Events)
Test the Application's Functionality and Connectivity to the new Database |  |  | Stewart Fohlo | Risk IT | 061 468 2979
Remediate any bugs or errors found during Application Testing |  |  | Stewart Fohlo & Vendor | Risk IT | 061 468 2979
Check if patches are installed and the server is uptodate |  |  | Stewart Fohlo | Risk IT | 061 468 2979
TEST ASSESSMENT
Has the change been tested in the Test Environment? | Yes | Yes, the app runs with a 2016 SQL DB
Has regression testing been successful? | No | N/A
Has the backout been tested in the test environment? | Yes | Yes
Has the change been tested & signed off by all impacted parties? | Yes | Yes
Has Business approval and TCR been Signed off, completed and Attached to the Remedy Change | Yes | N/A
BACKOUT / CONTINGENCY PLAN
Backout duration | 30 minutes
Backout / Contingency Tasks / Activities (Sequence of Events) | Start Time | End Time | Responsible Person | Area | Contact Details
Rollback- Pointing to the old SQL Database instance |  | 14h00 | Ilze Cloete | InMagic Vendor Support | 0713521987
Restart the Application |  | 15h00 | Ilze Cloete | InMagic Vendor Support | 0713521987
Backout / Contingency Post Implementation Testing (Sequence of Events) | Start Time | End Time | Responsible Person | Area | Contact Details
Test if the Application is starting Up |  |  | Stewart Fohlo | Risk IT | 061 468 2979
Login to the Application |  |  | Stewart Fohlo | Risk IT | 62 468 2979
Change Deployment Template